## Overview
SolSight — Project Overview
Open-source Solana memecoin signal-intelligence dashboard
Field | Detail
What it is | Rug screening, AI chart analysis (via Claude), wallet fund-flow mapping, and a community-voted signal feed for Solana memecoins. Next.js 15 App Router + TypeScript + Tailwind + Prisma + Postgres.
GitHub | github.com/2Pump/solsight (public)
Live deployment | https://solsight-eight.vercel.app (Vercel Hobby tier, project name: solsight)
Local dev folder | C:\Users\schid\OneDrive\Desktop\solsight (still on OneDrive — known file-lock risk)
Database | Neon Postgres, project solsight-db
Design language | Cyberpunk-styled dark UI, glass-panel cards, purple/teal signal accents
Core product principles
• Real data only — no mocked or simulated data anywhere in the app.
• Honest gaps — fields without a real data source yet show "Unknown", never a fake value.
• Direct, efficient communication and complete file deliveries over piecemeal patches.
• Ship functional product over polish.

## Features Built
Feature Area | Page / Location | What it does | Data Source | Status
Token detail & rug screening | /token/[address] | Live price, 24h change, market cap, volume; heuristic rug score (0-100) computed from real liquidity data; LP lock / mint & freeze authority / holder concentration honestly shown as "Unknown" until a real data source is wired up. | Birdeye (primary) → Dexscreener (fallback) | Verified
Price chart | /token/[address] | Candlestick chart of real OHLCV data with AI-identified key support/resistance levels drawn as price lines. | Birdeye OHLCV v3 | Verified
AI chart analysis | /token/[address] | Claude reads the real candle data and produces a bullish/bearish read with a confidence score and plain-language reasoning about price action, volume, and range. | Anthropic API (Claude) | Verified
Wallet fund-flow mapping | /wallet/[address] | Interactive node graph of a wallet's connected counterparties, transaction counts, and relative flow ranking based on the last 40 transactions. | Helius | Verified
Wallet search | /dashboard/wallets, /wallet/[address] | Look up any wallet by address; guards against pasting a token mint address by mistake. | Helius | Verified
Token search | /dashboard | Look up any Solana token by symbol/name and resolve it to its real mint address. | Dexscreener (keyless) | Verified
Signal feed | /feed | Community-facing feed of trading signals, queried directly from Postgres. | Neon Postgres (seeded, 2 sample signals so far) | Live but thin — needs real signal volume
Watchlist | /dashboard | Add/track tokens of interest. | Hardcoded sample data (Prisma tables exist, not yet wired up) | Not Started
Wallet connect / auth | App-wide | Wallet-based sign-in. | Privy (v3.35.1) | Verified

## Bugs Fixed
# | Bug / Difficulty | Root Cause | Fix Applied | Status
1 | CSS mask-image hiding page content | Applying the decorative .bg-signal-grid class directly to a content wrapper masked the content itself, not just the background. | Split the decorative grid into a separate empty sibling <div> across all 5 affected pages. | Fixed
2 | lightweight-charts v4 vs v5 API mismatch | Code used v5's addSeries(CandlestickSeries, ...) syntax while v4.2.2 was installed. | Switched to v4's addCandlestickSeries(...) syntax. | Fixed
3 | @headlessui/react incompatible with React 19 | Transitive dependency of an outdated Privy SDK pin (1.94.0). | Upgraded Privy to 3.35.1 (pulls headlessui v2); downgraded root React to 18.3.1 with a package.json "overrides" block forcing React 18.3.1 tree-wide as extra insurance. | Fixed
4 | Privy v3 config shape changed | embeddedWallets.createOnLogin moved to being nested per-chain in the new SDK version. | Updated to embeddedWallets: { solana: { createOnLogin: "users-without-wallets" } }. | Fixed
5 | Prisma watchlist bug | app/api/watchlist/route.ts used a non-existent compound unique key (userId_isDefault) papered over with an "as never" cast. | Rewrote using findFirst + create instead of the fake unique constraint. | Fixed
6 | Vercel security blocks on deploy | next and inngest versions had known CVEs that Vercel now hard-blocks. | Bumped next to 15.5.21 and inngest to 3.54.2. | Fixed
7 | Dependency tree peer conflicts | Real peer conflicts from mixed React 19/18 expectations across packages. | Added .npmrc with legacy-peer-deps=true; required for both local and Vercel installs to succeed. | Fixed
8 | Duplicate Vercel projects | Repeated re-imports created 6 separate solsight* Vercel projects. | Deleted down to a single project (solsight). | Fixed
9 | Cron schedule rejected on deploy | Vercel Hobby tier only allows daily cron jobs; vercel.json requested every-5-minutes. | Changed schedule from */5 * * * * to 0 6 * * *. | Fixed
10 | Wrong Helius base URL | Code called the deprecated api.helius.xyz endpoint. | Switched to api-mainnet.helius-rpc.com and added error logging so future failures show up in server logs instead of failing silently. | Fixed
11 | Deprecated Birdeye OHLCV endpoint | /defi/ohlcv is deprecated; also had wrong timeframe casing (Birdeye wants 1H/1D uppercase for hour/day, lowercase for minutes). | Switched to /defi/v3/ohlcv and fixed the case mapping. | Fixed
12 | Chart crash: "Cannot read properties of undefined (reading 'year')" | lightweight-charts requires strictly ascending, deduplicated, valid-number timestamps; some API responses returned slightly out-of-order or duplicate candle buckets. | Added defensive sort/filter/dedupe of candle data before setData() in price-chart.tsx. | Fixed
13 | Chart rendered completely blank for sub-cent tokens | The candlestick series defaults to priceFormat { precision: 2 }; a $0.00073 token rounds every OHLC value to $0.00, making every candle degenerate and breaking the chart's autoscale — with no error thrown. | Compute priceFormat precision dynamically from the smallest nonzero price actually present in the candle data, instead of trusting the library default. | Fixed
14 | Chart canvas rendering at 0x0 / never painting | autoSize: true relies on lightweight-charts' internal ResizeObserver, which doesn't reliably fire on first mount under React 18 Strict Mode's double-effect plus Turbopack dev's Fast Refresh — leaving the canvas sized 0x0 until a real browser resize event. | Size the chart explicitly from the container's getBoundingClientRect() at creation, and drive resizes with a dedicated ResizeObserver instead of the library's autoSize. | Fixed
15 | Chart appeared blank again after the above fixes | Not a chart bug at all — Birdeye was rate-limiting the API key (429 Too Many Requests) after a burst of manual test reloads during debugging, so getCandles() correctly returned an empty array with nothing to render. | Added a visible "No chart data could be rendered" empty-state message so future rate-limit hits are self-diagnosing from the UI alone, without needing devtools. Confirmed resolved once the rate limit window cleared. | Verified
16 | Node.js DEP0169 url.parse() deprecation warning in dev console | Generic Node 24+ deprecation warning from some transitive dependency's internal use of the legacy url API — not from any SolSight source code. | Confirmed benign (no CVEs, no functional impact); noted that running on Node 20 LTS instead of 24 would quiet it, matching the same Node version recommendation already made for sol-trader. | Deferred

## Next Steps
Priority | Item | Notes
High | Wire /dashboard watchlist to real Prisma tables | Currently hardcoded sample data; Watchlist/WatchlistItem tables already exist in the schema.
High | Build real on-chain rug-screening data | LP lock, mint authority, freeze authority, holder concentration all currently show "Unknown"; needs a Helius-based holder/authority lookup.
Medium | Auto-discover new/trending tokens | Signal feed DB currently only has 2 seeded tokens, making /feed thin. Consider a background job (Inngest is already in the stack).
Medium | Add retry/backoff for Birdeye 429s | getCandles()/getTokenOverview() currently return empty/null silently on rate-limit; a short retry-with-backoff would make transient rate limits invisible to users.
Low | Wallet Holdings panel — "Balance data unavailable" | Wallet fund-flow works; balance/holdings display still needs wiring up.
Low | $$WIF double-dollar-sign display bug | Cosmetic only.
Low | Empty leftover folder in repo | app/{dashboard,token[address],wallet[a...} — OneDrive won't delete it (permissions); harmless, safe to ignore.
Housekeeping | Move project off OneDrive | C:\Users\schid\OneDrive\Desktop\solsight has caused repeated file-lock issues; consider moving to C:\dev\solsight when convenient.
Housekeeping | Rotate pasted API keys | Anthropic, Neon, Privy, Birdeye, and Helius keys were pasted into a chat at one point; offer to rotate them stands whenever wanted.